## Sheet1
PLP Execution plan
Day | Activity | Deliverables | Phase
Day-1 | 1. Understand the Highlevel WBS, PLP phases and artifacts | 1. Detailed WBS | Requirement
| 2. Create project folder structure in SVN and learn working with SVN | 2. Understanding document
| 3. Prepare WBS | 3. Updated Query Tracking Sheet
| 4. Update Query tracking sheet. | 4. Minutes of Meeting(one sample)
5. Minutes of Meeting
Day-2 | 1. Presentation/update of understanding document to Mentor. | 1. Usecase, Class diagram | Design
| 2. Modify Class Diagram | 2. Sequence diagram (one sample)
| 3. Create usecase and sequence diagram | 3. DB design
| 4. DB Design and Screen Shots. | 4. Screens shots
5. Updated WBS
Day-3 | 1. Add functionality ,CTQ, nonfunctional test cases | 1. UTP(for one module only) | Design
2.Updated WBS
3. Traceability Matrix.(one module sample)
Day-4 | 1.LLD Preparation. | 1. Baselined HLD ,LLD and UTP | Design
| 2.Code Check list must be understood before starting the coding. | 2.Updated WBS,TimeSheet
Day-5 | Coding & Unit Testing(self testing) | Code | Coding
Day-6 | Self code review (PMD) , Peer Code review & Defect Fixing | 1. Code Review report, (for one module only) | Code Review
2. Code check list report(for one module only)
3.PMD report (for all modules)
3. Updated WBS
Day-7 | Peer testing & Defect Fixing | 1. Defect Tracking sheet(one module only) | Testing
2. Unit Test Report (one module only)
Day-8 | Integration, Integration Testing & Defect Fixing | Presentation PPT, war | Testing
Preparation of PPT and checking for all documents.
Day-9 | Final presentation | 1. Updated wbs | Presentation
2. Updated Query Tracking sheet
3. Use case Digram,Unders doc
3. HLD(CD,sq diagram,screens,DB)
4. LLD
5.Updated UTP
6.Traceability matrix
6 Updated review report and
7.Defect tracking sheet
8.Updated Timesheet
9.MoM(one sample)
10.deployed application(war)
11. Presentation PPT